IIR #2 Participant Pulse Question Form

***Identify your Government Function/Role: [Text response]

1. Planning Architecture and Common Understanding

Question:
Does the emerging planning architecture appear to provide a clear and credible foundation for organizing remaining scope, and did IIR #2 participants across Government, contractor, product, and functional organizations appear to share a common understanding of how that architecture supports IMS loading, PMB development, and recovery priorities?

Response:
☐ High Confidence
☐ Moderate Confidence
☐ Low Confidence
☐ Not Observed / Insufficient Basis

Prompts:

- What evidence increased or reduced confidence in the planning architecture?

- Did Government and contractor participants appear aligned on the purpose, structure, and use of the architecture?

- Were there areas where terminology, expectations, or understanding appeared inconsistent?

- Did governance and decision-making arrangements appear clear enough to support continued architecture maturation?

[Text Response]

Comments / Observations:

2. Scope, Ownership, and Accountability

Question:
Does the review provide confidence that remaining contractor scope is identified, organized, assigned, and traceable to requirements, deliverables, program commitments, and responsible organizations, and did the discussion show clear ownership, accountability, and willingness to resolve scope gaps or ambiguities?

Prompts:

- Were scope boundaries, ownership, and responsibilities clear?

- Were major program commitments, objectives, and deliverable expectations traceable through the planning architecture and understood consistently?

- Did participants acknowledge scope gaps, overlaps, or uncertainties where they existed?

- Did the review environment support candid discussion of unresolved scope or ownership issues?

Response:
☐ High Confidence
☐ Moderate Confidence
☐ Low Confidence
☐ Not Observed / Insufficient Basis

[Text Response]

Comments / Observations:

3. Planning Logic, Assumptions, and Evidence Quality

Question:
Did the contractor provide credible planning logic, duration rationale, QBD / quantity-based data, and task-development assumptions, and did the review discussion demonstrate openness to challenging, clarifying, or improving unsupported assumptions?

Prompts:

- Were planning assumptions and duration bases understandable and traceable?

- Were unsupported assumptions challenged or clarified?

- Did participants demonstrate a disciplined approach to improving planning evidence before IMS loading?

- Were there signs of pressure to accept weak rationale, incomplete evidence, or optimistic assumptions?

Response:
☐ High Confidence
☐ Moderate Confidence
☐ Low Confidence
☐ Not Observed / Insufficient Basis

[Text Response]

Comments / Observations:

4. Cross-Product / Cross-Function Integration and Coordination

Question:
Are major execution flows, interfaces, dependencies, supplier boundaries, Giver / Receiver relationships, and handoffs sufficiently visible, and did the review demonstrate effective cross-product / cross-function coordination to manage them?

Prompts:

- Were cross-product, cross-function, supplier, business-unit, or organizational dependencies clearly identified?

- Did the right participants appear to be engaged in resolving integration issues?

- Were handoffs and interfaces managed as shared execution issues rather than isolated product-team concerns?

- Were coordination needs, decision points, or unresolved dependencies visible enough to support follow-up?

Response:
☐ High Confidence
☐ Moderate Confidence
☐ Low Confidence
☐ Not Observed / Insufficient Basis

[Text Response]

Comments / Observations:

5. Risk, Assumption, Constraint, and Barrier Visibility

Question:
Were significant risks, assumptions, constraints, opportunities, supplier uncertainties, and organizational barriers made visible during IIR #2, and did participants appear willing and able to communicate them clearly for follow-up?

Prompts:

- Were risks and assumptions connected to planning decisions?

- Were organizational or communication barriers affecting planning maturity visible?

- Were supplier uncertainties, change-control implications, or unresolved dependencies discussed candidly?

- Were opportunities for improvement identified, or did the discussion focus only on problems?

Response:
☐ High Confidence
☐ Moderate Confidence
☐ Low Confidence
☐ Not Observed / Insufficient Basis

[Text Response]

Comments / Observations:

6. Leadership, Governance, Stakeholder Engagement, and Decision Environment

Question:
Did leadership actions, organizational priorities, governance mechanisms, stakeholder participation, and decision processes appear to support timely issue resolution, planning alignment, recovery progress, and continued maturation toward IMS loading and PMB implementation?

Prompts:

- Were priorities, decision paths, and expectations clear?

- Did leadership reinforce realism, integration, and issue resolution?

- Were the right Government, contractor, functional, supplier, and decision-making stakeholders engaged at the right level?

- Were any governance, participation, or decision-making barriers observed that could slow planning maturation?

Response:
☐ High Confidence
☐ Moderate Confidence
☐ Low Confidence
☐ Not Observed / Insufficient Basis

[Text Response]

Comments / Observations:

7. Overall Confidence and Recovery Environment

Question:
Overall, do the IIR #2 evidence, discussions, behaviors, organizational conditions, and recovery environment provide confidence that the contractor and Government are positioned to continue maturing the planning architecture toward IMS loading, PMB implementation, and follow-on IIRs?

Prompts:

- What most increased confidence?

- What most reduced confidence?

- What should leadership understand about the environment affecting planning maturation?

- Did the teams appear to have the people, data, tools, and analytical support needed to continue maturing the planning architecture after IIR #2?

- What should be carried forward into IIR #3, IIR #4, IIR #5, or IBR preparation?

[Text Response]

Response:
☐ High Confidence
☐ Moderate Confidence
☐ Low Confidence
☐ Not Observed / Insufficient Basis

Comments / Observations:

8. Optional Open-Ended Inputs

A. Top Strengths

Identify up to three strengths observed during IIR #2. These may include technical, planning, integration, leadership, communication, organizational, or environmental strengths.

- [Text response]

- [Text response]

- [Text response]

B. Top Concerns / Unknowns

Identify up to three concerns, unknowns, barriers, or issues requiring follow-up. These may include planning gaps, integration concerns, supplier uncertainties, communication issues, leadership concerns, organizational barriers, unresolved assumptions, or resource / tool / data limitations.

- [Text response]

- [Text response]

- [Text response]

C. Recommended Carry-Forward Items

Identify items that should remain visible after IIR #2.

| Carry-Forward Item | Suggested Destination |
| --- | --- |
| 1. [Text response] | ☐ IIR #3 ☐ IIR #4 ☐ IIR #5 ☐ IBR Prep ☐ Other |
| 2. [Text response] | ☐ IIR #3 ☐ IIR #4 ☐ IIR #5 ☐ IBR Prep ☐ Other |
| 3. [Text response] | ☐ IIR #3 ☐ IIR #4 ☐ IIR #5 ☐ IBR Prep ☐ Other |

D. Other Observations

Provide any additional observations that may help the Government understand planning maturity, integration risk, organizational readiness, communication effectiveness, leadership alignment, resource adequacy, tool / data limitations, or future review focus areas.

- [Text response]

- [Text response]

- [Text response]